## Slide 1
Replacement of the Research Cutter “UTHÖRN”
Michael Klages
21st ERVO Annual Meeting
June 11-13, 2019
Hamburg, Germany

## Slide 2: Uthörn – basic data
Keel laying: 1981 Commissioning: 8. September 1982
Dimensions: Length: 30.80 m Breadth: 8.50 m Draught: 2.65 m
Total weight: 274 t „Deadweight“: 87 t Bunker capacity: 39 t
Main tasks:
Transect cuises (monitoring) Day trips with up to 25 University students
Collecting organisms for courses Fishery surveys
Results of Lloyds Register Survey Report 2014
Regarding her age in good condition
There were no obvious material damages detected during inspection
Damages / malfunction at the propulsion system in thre future may cause immediate operational downtime because spare parts are not any longer available
Overall mechanical structure and machinery plant gives rise to an expected life-time at least until the end of 2020
However, a further prolongation of her classification at the end of 2021 is rather unlikely

## Slide 3
Our fleet is under renewal
Mya II - 2013

## Slide 4: Uthörn II – Boundary conditions
Board of Trustees and Scientific Advisory Board approved the project in 2018 with total costs of 10 Mio. €
The new „Uthörn“ shall have almost the same dimensions and functionalities as the existing one (length, draught, cruise speed, number of crew and scientists, etc)
As a regional class research vessel to be used in coastal research primarily for departments of Functional Ecology and Integrative Ecophysiology
Working areas are (primarily) the North Sea around Helgoland, and temporarily the Baltic Sea
With these boundary conditions in mind we expected to end up with a reasonable renewal.
But, in September 2018 our Naval Architects Bureau (Ship Design & Consult - SDC, Hamburg) informed us about a reply of the German Government to the inquiry of the parliamentary group BÜNDNIS90/Die Grünen from April 2018 about the Governments intention to reduce ships emissions on vessels under the responsibility of the Federation.

## Slide 5: Uthörn II – Boundary conditions
Answer by the Federal Ministry for Education and Science (BMBF):
„For possibly later new buildings of RV HEINCKE and UTHÖRN, with European operation areas, a LNG or Electric propulsion is to be provided“
Consequences regarding costs (preliminary estimates !):
100% electric drive (additional costs: 8.7 million €)
Optimized electric drive with range extension via an auxiliary diesel with exhaust after-treatment (additional costs: € 5.3 million)
LNG drive (additional costs: € 4.6 million)
(Bio) methanol drive (additional costs: 1.5 million €)

## Slide 6
RV „Electra“ University Stockholm
Built: 2016
Length: 24.3 m Breadth: 7.1 m
Draught: 2.2 m Speed.: 11 kn
Costs: 4.7 Mio. € inkl. MBS, SPS
Yard: Baltic Marine Workboat (Estonia)
Costs in 2021: 6.5 Mio € if 1:1 re-build
RV „Clupea“ BLE
Built: 2011
Length: 28.8 m. Breadth: 7.7 m
Draught: 2.3 m. Speed.: 11 kn
Costs: 13.5 Mio. €
Yard: Fassmer (Germany)
RV „Atair“ BSH – LNG
Build: ongoing
Length: 74 m Breadth:16.8 m
Draught: 5 m Speed: 13 kn
Costs: 140 Mio. €
Yard: Fassmer (Germany)
Remark – LNG needs space
Examples of some recent new buildings

## Slide 7: The next steps
Instead of developing our own ship design we will publish a Tender Call based on a Functional Description
We expect time and cost savings

## Slide 8: Mile stones
Mile stones | Objectives | Plan | Status
M1 | Selection of Naval Architect Bureau as Technical Advisor | Oct 18 | Finished
M2 | Presentation Functional Description of new "Uthörn" to main users for approval | Feb 19 | Finished
M3 | Publication of Tender Call (according to legal laws VGV§14 "not open procedure"; Negotiation procedure with participants competition) | Jun 19 | on time
M4 | Order with the selected yard signed | Dec 19 | 
M5 | Completing and approval of "Basic Design" | Feb 20 | 
M6 | Keel laying | Mar 20 | 
M7 | Completing and approval "Detailed Design" | May 20 | 
M8 | Ships hull and superstructures ready | Oct 20 | 
M9 | Technical installation (engines, cranes, A-frame, Bridge) completed | Feb 21 | 
M10 | Accommodations, lounges, galley etc. completed | Mar 21 | 
M11 | Scientific equipment and sensors installed (sonar systems, laboratories, winches etc) | Apr 21 | 
M12 | Electrical systems and on-board computer network ready laid and wired | May 21 | 
M13 | Factory Acceptance Tests (FAT) | Jun 21 | 
M14 | Completion of the "Uthörn" (remaining works, adjustments) | Jul 21 | 
M15 | Sea Acceptance Tests (SAT) on the North Sea | Aug 21 | 
M16 | Commissioning | Oct 21 | 

## Slide 9: Thank you for your attention