## Slide 1: How not to order a new research vessel
Niklas Andersson, coordinator

## Slide 2: RV Skagerak 4 years delayed
What have we learned?

## Slide 3: What has happened?
UGOT decided to build a new ship 2013, to be finished 2015
Tender call – cheap winning bid, with no profit for shipyard
Shipyard with no experience in completing complicated new builds
- But strong intention to start with special purpose vessels
Shipyard’s owners not interested in the new plans
6 Million euros increase of cost
Many disastrous delays and events: too heavy, unstable, crash
Addendum 1, 2, 3, 4 and 5 and X?

## Slide 4: What has happened?
Bankruptcy of subcontractor responsible for propulsion
But – still within budget
To be delivered September hopefully
49,5 meters long
11 meters wide
14 days endurance
Deplacement 1045 tonnes
5 person crew
Space for 16 scientists
Equipped with Multibeam, sub-bottom profiler, ADCP, CTD, box coring, multicoring, labs
Can support ROVs and AUV

## Slide 5: What have we learned?
Careful with tender call
Careful with politically managed shipyards
Maybe let external company do the project management
We should have negotiated at addendum 1
We should have paid the shipyard to use better equipment

## Slide 6: The future
We will recruit new vessel manager responsible for increasing the usage of the vessel
Aim to increase usage by 80 days per year